## Sheet1
Annual Report for WRRDA 2014 Section 1002 |  |  |  |  | Schedule Dates provided Sponsor: MM/DD/YY | [6 empty] | Revised Schedule Dates provided Sponsor: MM/DD/YY
Program Code | MSC | District | Study Name | Date of FCSA | Date Schedule sent to Sponsor | Release of draft Report (CW150) | District submits final feasibility report (CW160) | MSC transmittal of final report (CW260) | CWRB (CW245) | Signed Chief's Report (CW270) | Explanation of any missed deadlines | Date Explanation and Revised Schedule sent to sponsor | Release of draft Report (CW250) | District submits final feasibility report (CW160) | MSC transmittal of final report (CW260) | CWRB (CW245) | Signed Chief's Report (CW270) | Programs Notes
081730 | SWD | SWL | Three Rivers, AR | 2015-06-30 | 2015-09-02 | 2017-03-15 | 2018-02-01 | 2018-02-08 | 2018-02-23 | 2018-06-28 | No Change
081729 | SWD | SWT | Arkansas River Corridor | 2015-05-22 | 2015-05-10 | 2016-07-15 | 2016-11-23 | 2017-05-19 | 2017-07-03 | 2017-10-19 | No Change
081545 | SWD | SWG | Coastal Texas Protection | 2015-11-16 | 2016-02-02 | 2018-07-25 | 2020-10-20 | 2020-11-20 | 2021-01-22 | 2021-04-29 | No Change |  | 2018-07-25 | 2020-10-20 | 2020-11-20 | 2021-01-22 | 2021-04-29
006170 | SWD | SWG | Freeport GRR | 2015-06-10 | 2016-09-05 | 2017-03-02 | 2017-06-29 | 2017-07-17 | 2017-08-14 | 2017-11-03 | The delays in the study are attributed to a multitude of factors including, but not limited to: pilot concerns raised, scheduling issues with ship simulation facilities, comprehensive historical research on authorities, and changes in the dredged material management plan (DMMP) and economic assumptions. | 2017-06-05 | 2017-04-11 | 2018-01-08 | 2018-01-25 | 2018-03-28 | 2018-05-23 | General Reevaluation Report with amended FCSA 6/10/2015.
451958 | SWD | SWG | GIWW Brazos River Floodgates and Colorado River Locks | NA | NA | 2017-12-28 | 2018-08-30 | 2018-09-28 | 2018-12-12 | 2019-03-22 | No Sponsor to send letter to, create a MFR only | N/A | 2017-12-28 | 2018-08-30 | 2018-09-28 | 2018-12-12 | 2019-03-22 | GIWW has no FCSA or non federal sponsor cost sharing this study, vertical team alignment will occur at the AMM in Sep 16.
076185 | SWD | SWG | HGNC (Galveston Extension) | 2016-02-29 | 2016-09-01 | 2013-03-01 | 2016-09-26 | 2016-10-07 | 2016-11-09 | 2017-04-07 |  | 2017-07-21 | Legacy | 2016-12-09 | 2016-12-16 | 2017-02-09 | 2017-07-31 | Legacy study with change in sponsorship scoped to completion after FCSA signed in 2/29/2016
007780 | SWD | SWG | Houston Ship Channel | 2015-11-13 | 2016-02-16 | 2017-05-18 | 2019-05-10 | 2019-06-10 | 2019-07-12 | 2019-10-28 | On, January 27, 2017, the senior leader panel concurred that due to the complexity of the study involving numerous design vessels and potential channel modifications needed to ease pilot rules and restrictions, additional time would be necessary to analyze costs and benefits to identify the Tentatively Selected Plan (TSP). The additional time resulted in a delay in the schedule to release the draft feasibility report. All other milestones remain as scheduled. | 2017-08-08 | 2017-09-01 | 2019-05-10 | 2019-06-10 | 2019-07-12 | 2019-10-28
010625 | SWD | SWF | Sulphur River Basin | 2012-04-03 | 2013-11-22 | 2015-11-13 | 2016-04-29 | 2016-05-20 | 2016-06-17 | 2016-08-31 | Exemption request required to document additional Dam Safety and Reallocation studies. Updated Milestone schedule will be provided to sponsors upon approval of exemption.
013501 | SWD | SWF | Guadalupe and San Antonio River Basins, TX (Lower Guadalupe) | 2013-03-15 | 2013-09-01 | 2015-02-28 | 2015-05-05 | 2015-05-31 | 2015-07-15 | 2015-08-31 | Exemption request required to document study rescoping to incorporate damage areas from the May 2015 flood event. Updated milestone schedule will be provided to sponsors upon approval of exemption.
012952 | SWD | SWF | Middle Brazos River, TX | 2005-12-01 | 2015-07-16 | 2016-06-09 | 2016-11-01 | 2016-11-21 | 2017-01-05 | 2017-03-09 | Legacy study required exemption and compliance memo to incorporate rescoped study.
445800 | SWD | SWG | Jefferson County Shore Protection | 2016-07-08 | 2016-11-14 | 2017-03-15 | 2017-09-15 | 2017-10-16 | 2017-12-15 | 2018-03-31 | Timeline chg'd back to 3x3x3 and initial guidance suggested the 3 year timeline would begin upon receipt of federal funds however, the guidance later clarified to begin upon signing of the FCSA. | 2017-07-14 | 2018-03-15 | 2019-01-09 | 2019-02-07 | 2019-04-04 | 2019-07-09 | FCSA Signed 7/8/2016 PDT is working on scoping and schedule to be provided within 90 days. 10/12/16 - Need PMP to produce schedule, can't send letter until this happens
451954 | SWD | SWG | Matagorda Ship Channel, TX | 2016-08-05 | 2016-12-05 | 2018-04-10 | 2019-01-07 | 2019-02-05 | 2019-04-17 | 2019-07-17 | No Change |  | 2018-04-10 | 2019-01-07 | 2019-02-05 | 2019-04-17 | 2019-07-17 | FCSA Signed 8/5/2016 PDT is working on scoping and schedule to be provided within 90 days. 10/12/16 - Need PMP to produce schedule, can't send letter until this happens. PMP dated Dec 2016 and signed Jan 2017
013592 | SWD | SWG | Resacas at Brownsville | 2015-08-12 | 2015-11-09 | 2017-02-22 | 2017-11-14 | 2017-12-13 | 2018-03-16 | 2018-06-28 | Initial schedule was based on assumption of full-funding (Federal and non-Federal) over the course of the study. Workplan funds were not received until Jun 2017. The PDT members were drawn into the Mississippi flood fighting mission which also contributed to the schedule slippage. | 2017-08-10 | 2017-06-08 | 2018-01-24 | 2018-02-21 | 2018-05-16 | 2018-08-13 | Actual for CW150 was 2/28/17
014363 | SWD | SWG | Sabine Pass to Galveston Bay | 2013-01-10 | 2015-09-10 | 2015-09-11 | 2016-04-15 | 2016-05-20 | 2016-07-12 | 2016-09-27 | Exemption approved on 1 June 2016 supported additional H&H modeling and Engineer design to reduce risk uncertainty for the tenatively selected plan. The additional engineering analyses, preparation of the final report and the conduct of the Civil Works Review Board required a few more weeks than expected. | 2017-07-14 | 2015-09-11 | 2017-03-02 | 2017-03-09 | 2017-05-10 | 2017-08-31 | Exemption approved on 1 June 2016 supported additional H&H modeling and Engineer design to reduce risk uncertainty for the tenatively selected plan.
BLUE FONT = COMPLETED