## Year 3 - FY17
| Table 1: Schedules and Missed Milestone Explanations | [5 empty] | Schedule Dates Provided Sponsor | [6 empty] | Revised Schedule Dates Provided Sponsor
Program | MSC | District | Program Code | Study Name | FCSA | Date letter sent | Release of Draft Report | District Submits Final Feasibility Report | MSC Transmittal of Final Report | Civil Works Review Board | Signed Chief's Report | Explanation of any missed milestones or schedule adjustments | Date explanation and revision | Release of Draft Report | District Submits Final Feasibility Report | MSC Transmittal of Final Report | Civil Works Review Board2 | Signed Chief's Report
| LRD |  |  | Du Page River, IL | 2015-07-01 | 2015-12-29 | 2017-05-05 | 2017-12-15 | 2018-02-26 | 2018-04-20 | 2018-07-13
| LRD |  |  | Ecorse Creek, MI | 2009-10-01 | 2015-06-12 | 2016-11-26 | 2017-07-14 | 2017-08-14 | 2017-10-12 | 2018-03-09
| LRD |  |  | Saginaw River Deepening, Saginaw , MI | 2009-10-01: 2014-12-15
| MVD | B4 - MVK |  | Big Sunflower River Watershed, Quiver River, Mississippi | 2011-09-23 |  | 2016-10-21 | 2017-09-17 | 2017-10-17 | 2017-12-07 | 2018-03-29
| MVD |  |  | Brandon Road, Interbasin Control of Great Lakes Mississippi River Aquatic Nuisance Species, IL, IN, OH, WI |  |  | 2017-02-22 | 2018-01-19 | 2018-05-18 | 2018-07-20 | 1/18/019
| MVD |  |  | Kaskaskia River Basin, IL | 2015-09-15 | 2016-01-27 | 2017-06-29 | 2018-03-30 | 2018-04-30 | 2018-06-30 | 2018-09-30
| MVD | B2 - MVN |  | Louisiana Coastal Area (LCA) Mississippi River Hydrodynamic and Delta Management Study | 2015-09-15: 2011-08-24
| MVD | B1 - MVM |  | Memphis Metro: Cypress Creek, TN | 2015-09-15: 2014-08-01 |  | 2016-09-19
| MVD | B2 - MVN |  | Mississippi River Ship Channel, Gulf to Baton Rouge, LA | 2015-04-15 | 2015-06-30 | 2016-11-10 | 2017-09-20 | 2017-10-27 | N/A** | N/A**
| MVD |  |  | Souris River Basin, ND |  |  | 2017-09-29 | 2018-09-28 | 2018-10-31 | 2018-12-31 | 2019-04-30
010446 | MVD |  |  | St. Croix River, WI | NA**** | NA | 2016-12-09 | 2017-01-16 | 2017-02-16 | NA** | NA**
| MVD | B3 - MVS |  | St. Louis Riverfront Meramec/Big River/St. Louis Mississippi River Front, MO, IL | 2015-08-27 | 2015-11-02 | 2017-04-28 | 2017-11-24 | 2018-01-26 | 2018-04-13 | 2018-08-03
| NAD |  |  | CITY OF NORFOLK, VA (SANDY FOCUS AREA) (Flood Risk Management Studies, Norfolk, VA)
| NAD |  |  | Fairfield and New Haven Counties, CT
| NAD |  |  | NASSAU CITY (SANDY FOCUS AREA)
| NAD |  |  | New Jersey Back Bay - (Sandy Focus Area)
| NAD |  |  | New York and New Jersey Harbor and Tributaries (Sandy Focus Area)
| NAD |  |  | RARITAN RIVER BASIN, GREEN BROOK SUB-BASIN, NJ (UPPER BASIN)
| NAD |  |  | UPPER SUSQUEHANNA COMPREHENSIVE FLOOD DAMAGE REDUCTION, NY
| NAD |  |  | NEW HAVEN HARBOR DEEPENING, CT
| NAD |  |  | New York and New Jersey Harbor, NY & NJ
| NAD |  |  | THE DISTRICT OF COLUMBIA, DC (Sandy Focus Area)
| NAD |  |  | Anacostia Watershed Restoration, Prince Georges County, MD | 2015-08-27: 2014-01-13 |  | 2016-09-26
| NAD |  |  | Baltimore 50-Foot Channel, MD and VA
| NAD |  |  | Del River Dredge Material Utilization, Delaware* |  |  | 2016-09-23 | 2017-03-21 | 2017-04-28 | 2017-06-23 | 2017-09-07
| NAD |  |  | Del River Dredge Material Utilization, NJ* |  |  | 2016-09-23 | 2017-03-21 | 2017-04-28 | 2017-06-23 | 2017-09-07
| NAD |  |  | Fire Island to Montauk Point (FIMP) Reformulation, NY* | [8 empty] | 2016-09-26
| NAD | NAO |  | Flood Risk Management Studies, Norfolk, VA | 2016-02-03 | 5/9/2016 | 2017-10-03 | 2018-06-14 | 2018-07-19 | 2018-10-18 | 2019-01-31
| NAD |  |  | Hashamomuck Cove, NY* | [8 empty] | 2016-09-26
| NAD |  |  | Highlands, NJ* | [8 empty] | 2016-09-26
| NAD |  |  | Hudson Raritan Estuary - Jamaica Bay, NY, Environmental | 2015-08-27: 1996-02-01 |  | 2016-09-26
| NAD |  |  | Hudson Raritan Estuary - Bronx River Basin, NY | 2015-08-27: 2003-11-01 |  | 2016-09-26
| NAD |  |  | Hudson Raritan Estuary - Flushing Bay, NY | 2015-08-27: 1999-09-01 |  | 2016-09-26
| NAD |  |  | Hudson Raritan Estuary - Hackensack | 2015-08-27: 2003-04-23 |  | 2016-09-26
| NAD |  |  | Hudson Raritan Estuary - Lower Passaic River, NJ | 2015-08-27: 2003-06-30 |  | 2016-09-26
| NAD |  |  | Hudson Raritan Estuary NY &NJ | 2015-08-27: 2001-07-12 |  | 2016-09-26
| NAD |  |  | Lake Montauk Harbor, NY* | [8 empty] | 2016-09-26
| NAD |  |  | Mamaroneck-Sheldrake Rivers, NY | 2015-08-27: 2010-03-01 |  | 2016-09-26
| NAD | NAP |  | New Jersey Backbay Coastal Resilience Study, NJ | 2016-04-11 | 2016-09-09 | 2017-12-26 | 2018-09-02 | 2018-11-02 | 2018-12-18 | 2019-04-05
| NAD |  |  | Norfolk Harbor 55-Foot Channel, VA |  |  | 2017-03-01 | 2017-11-22 | 2017-12-22 | 2018-03-01 | 2018-06-01
| NAD |  |  | Norfolk Harbor, Eliz River South Branch, VA |  |  | 2017-03-01 | 2017-11-22 | 2017-12-22 | 2018-03-01 | 2018-06-01
| NAD |  |  | North Shore of Long Island, Asharoken, NY* | [8 empty] | 2016-09-26
444053 | NAD |  |  | Passaic River Tidal Protection Area* | [8 empty] | 2016-09-26
444633 | NAD |  |  | Pawcatuck River & Rhode Island Coastal Investigation* |  |  | 2016-10-14 | 2017-03-31 | 2017-05-02 | 2017-06-29 | 2017-10-12
| NAD |  |  | Rahway River Basin, NJ | [8 empty] | 2016-09-26
| NAD |  |  | Rahway River Basin, NJ* | [8 empty] | 2016-09-26
| NAD |  |  | Rockaway, NY* | [8 empty] | 2016-09-26
| NAD |  |  | Shrewsbury, NJ* | [8 empty] | 2016-09-26
| NAD |  |  | South Shore of Staten Island, NY* |  |  | 2015-06-12 | 2016-04-27 | 2016-06-20 | N/A | 2016-10-31
013592 | NAD |  |  | Westchester County Streams, Byram River, NY | 2016-04-11: 2012-08-29 |  | 2016-09-26
| NWD |  |  | Adams and Denver County, CO | 2016-04-11: 2014-05-20 |  | 2016-09-23
010625 | NWD |  |  | Fremont, NE | 2015-07-21 | 2016-08-10 | 2017-04-05 | 2017-12-05 | 2018-01-05 | 2018-03-15 | 2018-06-15
| NWD |  |  | Grand River Basin, MO
| NWD |  |  | Lower Dungeness Ecosystem Restoration Study, WA | 2016-03-17 | 2016-08-30 | 2018-01-11 | 2019-05-24 | 2019-06-27 | 2019-09-20 | 2020-01-08
| NWD |  |  | Missouri River Bed Degradation, MO | 2010-11-01 | 2012-11-05 | 2017-01-31 | 2017-03-20 | 2017-04-10 | 2017-08-25 | 2017-12-12
13767 | NWD |  |  | Puyallup River Basin Flood Risk Management Feasibility Study, WA | 2010-11-01: 2010-09-23 |  | 2016-09-23
| NWD |  |  | Seattle Harbor Navigation Improvement Project General Investigation Study, WA | 2014-09-29 | 2014-09-29 | 2016-08-02 | 2017-03-15 | 2017-04-14 | 2017-06-15 | 2017-09-29
007780 | NWD |  |  | Willamette River Basin Review, OR | 2015-08-19 | 2015-09-29 | 2017-08-08 | 2018-01-31 | 2018-02-28 | 2018-05-18 | 2018-08-17
| POD |  |  | Ala Wai Canal, HI | 2012-11-08 | 2015-06-09 | 2015-09-01 | 2016-07-01 | 2016-08-01 | 2016-10-01 | 2017-01-01
076185 | POD |  |  | Kenai Bluffs, AK | 2015-05-12 | 2015-08-10 | 2017-03-28 | 2017-05-26 | 2017-06-12 | NA** | NA**
| POD | POA |  | Kotzebue Navigation Improvement, AK | 2015-11-12 | 2016-02-16 | 2017-05-15 | 2018-05-21 | 2018-05-30 | 2018-07-31 | 2018-10-01
| POD |  |  | Lowell Creek Tunnel Flood Diversion, AK
397427 | POD | POH |  | Rota Harbor, CNMI | 2015-12-04 | 2016-03-16 | 2017-07-07 | 2018-05-21 | 2018-06-12 | 2018-09-12 | 2019-01-07
| POD | POA |  | St. George Navigation Improvement, AK | 2015-10-15 | 2016-02-18 | 2017-05-17 | 2018-04-25 | 2018-05-09 | 2018-07-11 | 2018-09-15
| POD | POH |  | Tinian Harbor, CNMI | 2015-12-04 | 2016-03-16 | 2017-07-07 | 2018-05-21 | 2018-06-12 | 2018-09-12 | 2019-01-07
| POD |  |  | Unalaska (Dutch) Harbor, AK
| SAD | SAJ |  | Loxahatchee River Watershed Restoration | 1/21/16*** | 2015-12-18 | 2017-08-10 | 2018-06-12 | 2018-08-03 | 2018-09-24 | 2019-01-09
010447 | SAD | SAM |  | Mobile Harbor, AL | 11/9/2015** | 2016-01-20 | 2018-07-18 | 2019-04-11 | 2019-05-21 | NA** | NA**
| SAD | SAM |  | Proctor Creek, GA | 2015-10-05 | 2015-12-22 | 2017-07-10 | 2018-03-19 | 2018-04-18 | 2018-06-18 | 2018-09-18
| SAD | SAJ |  | San Juan Harbor Improvements Study | 2015-09-16 | 2015-12-17 | 2017-03-03 | 2018-03-15 | 2018-04-15 | 2018-06-15 | 2018-09-14
| SAD |  |  | Savannah River Below Augusta Ecosystem Restoration, GA
| SAD | SAJ |  | St. Johns County Feasibility | 2004-09-22 | 2015-08-07 | 2016-02-17 | 2016-11-22 | 2016-12-22 | 2017-02-22 | 2017-05-22
081545 | SAD | SAJ |  | St. Lucie County Feasibility | 2004-06-29 | 2015-08-07 | 2016-05-03 | 2016-12-06 | 2017-02-07 | 2017-04-07 | 2017-07-07
13838 | SAD | SAM |  | Sweetwater Creek, GA | 2016-05-25 | 2016-08-23 | 2018-03-13 | 2018-10-30 | 2018-11-30 | 2019-01-30 | 2019-04-29
| SPD |  |  | Aliso Creek Mainstem, CA
| SPD |  |  | Arroyo Seco Watershed, CA
| SPD | SPL |  | Carpinteria, CA | 2003-06-26 | 2016-08-19 | 2018-08-06 | 2019-03-12 | 2019-04-12 | 2019-06-11 | 2019-09-10
| SPD |  |  | Corte Madera Creek, CA |  |  | 2017-03-10 | 2018-02-05 | 2018-03-05 | 2018-05-07 | 2018-08-07
| SPD |  |  | Dry Creek (Warm Springs) Restoration, CA |  |  | 2017-05-19 | 2018-04-10 | 2018-05-10 | 2018-07-10 | 2018-10-10
| SPD | SPL |  | East San Pedro Bay, CA | 2010-11-10 | 2016-08-19 | 2017-10-23 | 2018-07-30 | 2018-08-30 | 2018-10-30 | 2019-02-07
| SPD |  |  | Espanola Valley, Rio Grande and Tributaries, NM
| SPD |  |  | Little Colorado (Winslow), AZ
| SPD |  |  | Lower San Joaquin, CA | [8 empty] | 2016-09-13
| SPD | SPL |  | Lower Santa Cruz River, CA | 2015-08-28 | 2016-08-19 | 2017-12-31 | 2019-02-27 | 2019-03-29 | 2019-05-31 | 2019-08-30
| SPD | SPL |  | Malibu Creek Watershed, CA | 2001-07-30 | 2016-08-19 | 2016-12-30 | 2017-08-30 | 2017-09-29 | 2017-11-29 | 2018-03-09
| SPD |  |  | Middle Rio Grande Bernalillo to Belen | [8 empty] | 2016-09-22
| SPD |  |  | North West El Paso Feasibility Study, NM | [8 empty] | 2016-09-22
| SPD |  |  | Pajaro River, CA | [8 empty] | 2016-09-23
114479 | SPD | SPL |  | Port of Long Beach Navigation Improvements, CA | 2015-08-27 | 2016-08-19 | 2017-04-30 | 2018-01-29 | 2018-02-28 | 2018-04-30 | 2018-07-30
13010 | SPD | SPL |  | Prado Basin, CA | [8 empty] | 2016-09-21
| SPD |  |  | Rio Grande, Sandia Pueblo to Isleta Pueblo, NM
| SPD |  |  | Sacramento Bank Protection GRR, CA |  |  | 2017-03-03 | 2017-11-15 | 2017-12-15 | 2018-02-02 | 2018-06-29
| SPD |  |  | San Francisco Bay to Stockton, CA | [8 empty] | 2016-09-23
| SPD |  |  | San Francisquito Creek, CA | [8 empty] | 2016-09-23
| SPD |  |  | San Joaquin Delta Islands and Levees, CA
| SPD |  |  | Truckee Meadows, NV GRR
014363 | SPD | SPL |  | Westminster, CA (East Garden Grove) | [8 empty] | 2016-09-21
081730 | SPD |  |  | Yuba River Ecosystem Restoration, CA |  |  | 2016-12-20 | 2017-08-29 | 2017-09-25 | 2017-11-28 | 2018-06-02
| SWD | SWT |  | Arkansas River Corridor | 2015-05-22 | 2015-05-10 | 2017-02-06 | 2017-09-25 | 2017-10-17 | 2018-01-23 | 2018-04-12
| SWD | SWG |  | Coastal Texas Protection, TX | 2015-11-16 | 2016-02-02 | 2018-07-25 | 2020-10-20 | 2020-11-20 | 2021-01-22 | 2021-04-29 | No Change | N/A | 2018-07-25 | 2020-10-20 | 2020-11-20 | 2021-01-22 | 2021-04-29
| SWD | SWG |  | Freeport Harbor, TX | 2015-06-10 | 2016-09-05 | 2017-03-02 | 2017-06-29 | 2017-07-17 | 2017-08-14 | 2017-11-03 | The delays in the study are attributed to a multitude of factors including, but not limited to: pilot concerns raised, scheduling issues with ship simulation facilities, comprehensive historical research on authorities, and changes in the dredged material management plan (DMMP) and economic assumptions. | 2017-06-05 | 2017-04-11 | 2018-01-08 | 2018-01-25 | 2018-03-28 | 2018-05-23
| SWD | SWG |  | GIWW - Brazos River Floodgates & Colorado River Lock, TX | N/A | N/A | 2017-12-28 | 2018-08-30 | 2018-09-28 | 2018-12-12 | 2019-03-22 | No Change | N/A | 2017-12-28 | 2018-08-30 | 2018-09-28 | 2018-12-12 | 2019-03-22
| SWD | SWG |  | Houston Galveston Navigation Channels Extension | 2016-02-29 | 2016-09-01 | 2013-03-01 | 2016-09-26 | 2016-10-07 | 2016-11-09 | 2017-04-07 | A delay in initiating State and Agency Review resulted in a subsequent schedule delay for signing the Chief's report. | 2017-07-21 | Legacy | 2016-12-09 | 2016-12-16 | 2017-02-09 | 2017-07-31
| SWD | SWG |  | Houston Ship Channel, TX | 2015-11-13 | 2016-02-16 | 2017-09-01 | 2019-05-10 | 2019-06-10 | 2019-07-12 | 2019-10-28 | On, January 27, 2017, the senior leader panel concurred that due to the complexity of the study involving numerous design vessels and potential channel modifications needed to ease pilot rules and restrictions, additional time would be necessary to analyze costs and benefits to identify the Tentatively Selected Plan (TSP). The additional time resulted in a delay in the schedule to release the draft feasibility report. All other milestones remain as scheduled. | 2017-08-04 | 2017-09-01 | 2019-05-10 | 2019-06-10 | 2019-07-12 | 2019-10-28
| SWD | SWG |  | Jefferson County Shore Protection | 2016-07-08 | 2017-07-14 | 2018-03-15 | 2019-01-09 | 2019-02-07 | 2019-04-04 | 2019-07-09 | Timeline chg'd back to 3x3x3 and initial guidance suggested the 3 year timeline would begin upon receipt of federal funds however, the guidance later clarified to begin upon signing of the FCSA. | 2017-07-14 | 2018-03-15 | 2019-01-09 | 2019-02-07 | 2019-04-04 | 2019-07-09
| SWD | SWG |  | Matagorda Ship Channel (Widening and Deepening), TX | 2016-08-05 | 2016-12-05 | 2018-04-10 | 2019-01-07 | 2019-02-05 | 2019-04-17 | 2019-07-17 | No Change | N/A | 2018-04-10 | 2019-01-07 | 2019-02-05 | 2019-04-17 | 2019-07-17
| SWD | SWF |  | Middle Brazos River, TX | 2016-08-05: 2005-12-01 |  | 2016-09-16
| SWD | SWG |  | Resacas at Brownsville | 2015-08-12 | 2015-11-09 | 2017-02-22 | 2017-11-14 | 2017-12-13 | 2018-03-16 | 2018-06-28 | Initial schedule was based on assumption of full-funding (Federal and non-Federal) over the course of the study. Workplan funds were not received until Jun 2017. The PDT members were drawn into the Mississippi flood fighting mission which also contributed to the schedule slippage. | 2017-08-04 | 2017-06-08 | 2018-01-24 | 2018-02-21 | 2018-05-16 | 2018-08-13
| SWD | SWG |  | Sabine Pass to Galveston Bay | 2013-01-10 | 2015-09-10 | 2015-10-26 | 2017-02-06 | 2017-02-13 | 2017-04-11 | 2017-08-01 | Exemption approved on 1 June 2016 supported additional H&H modeling and Engineer design to reduce risk uncertainty for the tenatively selected plan. The additional engineering analyses, preparation of the final report and the conduct of the Civil Works Review Board required a few more weeks than expected. | 2017-07-14 | 2015-09-11 | 2017-03-02 | 2017-03-09 | 2017-05-10 | 2017-08-31
081729 | SWD | SWF |  | Sulphur River Basin | 2013-01-10: 2012-04-03 |  | 2016-09-16
| SWD | SWL |  | Three Rivers, AR | 2015-06-30 | 2015-09-02 | 2017-02-09 | 2018-01-18 | 2018-02-15 | 2018-03-27 | 2018-06-29
**** Milestone not required
| * |  |  | Sandy Supplemental Funded Studies
| ** |  |  | Milestone is not required

## Year 2 - FY16
| Table 1: Schedules and Missed Milestone Explanations |  |  |  |  | Schedule Dates Provided Sponsor | [6 empty] | Revised Schedule Dates Provided Sponsor
Program | MSC | District | Study Name | FCSA | Date letter sent | Release of Draft Report | District Submits Final Feasibility Report | MSC Transmittal of Final Report | Civil Works Review Board | Signed Chief's Report | Explanation of any missed milestones or schedule adjustments | Date explanation and revision | Release of Draft Report | District Submits Final Feasibility Report | MSC Transmittal of Final Report | Civil Works Review Board2 | Signed Chief's Report
| LRD |  | Blanchard River Watershed Study | 2008-09-30 | 2015-08-26 | 2015-04-10 | 2015-11-09 | 2015-12-11 | 2016-02-19 | 2016-05-28 | The feasibility study is terminating, no vertically approved schedule to report.
| LRD |  | Du Page River, IL | 2015-07-01 | 2015-12-29 | 2017-05-05 | 2017-12-15 | 2018-02-26 | 2018-04-20 | 2018-07-13
| LRD |  | Ecorse Creek, MI | 2009-10-01 | 2015-06-12 | 2015-11-10 | 2016-07-20 | 2016-10-11 | 2017-01-21 | 2017-04-12 | The milestones were delayed due to limited resources, current vertically approved schedule is reported. | 2016-08-22 | 2016-11-26 | 2017-07-14 | 2017-08-14 | 2017-10-12 | 2018-03-09
| LRD |  | Mill Creek, Tennessee Feasibility Study | 2003-04-23 | 2015-05-05 | 2014-10-30 | 2015-02-03 | 2015-02-17 | 2015-05-28 | 2015-08-20 | The feasibility study is completed, actual dates reported. | 2015-09-15 | 2014-10-30 | 2015-02-03 | 2015-02-17 | 2015-05-28 | 10/16/2015
| LRD |  | Saginaw River Deepening, Saginaw , MI | 2014-12-15 | 2015-02-23 | 2017-09-18 | 2017-10-24 | 2017-12-07 | 2018-01-23 | 2018-05-08 | No missed milestones, however the study is under review and there is not a current schedule available to report.
| MVD | B4 - MVK | Big Sunflower River Watershed, Quiver River, Mississippi | 2011-09-23 |  | 2015-09-02 | 2016-06-09 | 2016-07-24 | 2016-10-07 | 2017-01-27 | The release of the Draft Report was delayed due to the inclusion of the Locally Preferred Plan. | 2016-09-19 | 2016-10-21 | 2017-09-17 | 2017-10-17 | 2017-12-07 | 2018-03-29
| MVD |  | Brandon Road, Interbasin Control of Great Lakes Mississippi River Aquatic Nuisance Species, IL, IN, OH, WI |  |  | 2017-02-22 | 2018-01-19 | 2018-05-18 | 2018-07-20 | 1/18/019
| MVD | B5 - MVR | Des Moines Levee System, Des Moines and Raccoon Rivers, IA | 2015-08-18 | 2016-01-14 | Aug 2016 | Jun 2017 | Aug 2017 | Oct 2018 | Jan 2018 | The feasibility study is terminating, no schedule to report. | 2016-09-19: 2016-08-30
| MVD |  | Kaskaskia River Basin, IL | 2015-09-15 | 2016-01-27 | 2017-06-29 | 2018-03-30 | 2018-04-30 | 2018-06-30 | 2018-09-30
| MVD | B2 - MVN | Louisiana Coastal Area (LCA) Mississippi River Hydrodynamic and Delta Management Study | 2011-08-24 | 2015-06-22 | N/A | N/A | 2016-11-16 | 2017-01-30 | 2017-04-28 | Sponsor submitted permit request for major components under consideration by the study. Study is pending agreement on the path forward, no vertically aligned schedule to report.
| MVD | B1 - MVM | Memphis Metro: Cypress Creek, TN | 2014-08-01 | 2015-06-10 | 2015-10-02 | 2016-04-15 | 2016-06-10 | 2016-09-16 | 2016-12-23 | Additional time needed on delivery of the modeling by the sponsor due to updated LiDAR. Study is under review, no vertically aligned schedule to report. | 2016-09-19
| MVD | B2 - MVN | Mississippi River Ship Channel, Gulf to Baton Rouge, LA | 2015-04-15 | 2015-06-30 | 2016-11-10 | 2017-09-20 | 2017-10-27 | N/A | 2018-03-30 | No missed milestones, schedule has been adjusted since there is no Chiefs Report expected. |  | 2016-11-10 | 2017-09-20 | 2017-10-27 | N/A** | N/A**
| MVD |  | Souris River Basin, ND |  |  | 2017-09-29 | 2018-09-28 | 2018-10-31 | 2018-12-31 | 2019-04-30
| MVD |  | Southwest Coastal Louisiana Feasibility Study | 2009-01-14 | 2015-06-22 | N/A | 2015-08-28 | 2015-10-09 | 2015-12-08 | 2016-03-25 | The feasibility study is completed, actual dates reported. | 2015-12-02 | 2015-03-20 | 2016-01-29 | 2016-02-29 | 2016-04-21 | 2016-07-29
010446 | MVD |  | St. Croix River, WI | NA**** | NA | 2016-12-09 | 2017-01-16 | 2017-02-16 | NA** | NA**
| MVD | B3 - MVS | St. Louis Riverfront Meramec/Big River/St. Louis Mississippi River Front, MO, IL | 2015-08-27 | 2015-11-02 | 2017-04-28 | 2017-11-24 | 2018-01-26 | 2018-04-13 | 2018-08-03
| NAD |  | Anacostia Watershed Restoration, Montgomery County, MD | 2013-10-08 | 2015-06-18 | 2015-08-10 | 2016-01-27 | 2016-02-23 | 2016-05-18 | 2016-09-20 | Terminating study and completing in the Continuing Authorities Program, no vertically aligned schedule to report.
| NAD |  | Anacostia Watershed Restoration, Prince Georges County, MD | 2014-01-13 | 2015-06-18 | 2015-10-06 | 2016-04-08 | 2016-05-06 | 2016-08-01 | 2016-12-14 | The milestones were delayed due to plan optimization concerns and the time required to address these technical issues. The Draft report was released on 6/1/2016. A vertically aligned schedule is not available to report at this time. | 2016-09-26
| NAD |  | Baltimore 50-Foot Channel, MD and VA |  |  | 2016-01-14 | 2016-11-01 | 2016-12-01 | 2017-02-23 | 2017-08-10 | Feasibility study terminating, study will proceed as a validation study, no vertically aligned schedule to report.
| NAD |  | Del River Dredge Material Utilization, Delaware* |  |  | 2016-05-11 | 2016-12-20 | 2017-02-07 | 2017-04-05 | 2017-06-29 | The release of the Draft Report milestone was missed due to time required to complete complex modeling used to analyze economic benefits, the revised schedule is reported. | 2016-06-10 | 2016-09-23 | 2017-03-21 | 2017-04-28 | 2017-06-23 | 2017-09-07
| NAD |  | Del River Dredge Material Utilization, NJ* |  |  | 2016-05-10 | 2016-12-29 | 2017-02-06 | 2017-04-04 | 2017-06-28 | The release of the Draft Report milestone was missed due to time required to complete complex modeling used to analyze economic benefits, the revised schedule is reported. | 2016-06-10 | 2016-09-23 | 2017-03-21 | 2017-04-28 | 2017-06-23 | 2017-09-07
402964 | NAD |  | Delaware River Comp, NJ* |  |  | 2015-07-24 | 2016-08-31 | 2016-10-06 | 2016-12-09 | 2017-04-13 | Study suspended per sponsor's request, no schedule to report.
| NAD |  | Fire Island to Montauk Point (FIMP) Reformulation, NY* |  |  | 2016-01-29 | 2016-07-08 | 2016-08-12 | 2016-10-19 | 2017-01-06 | The release of the Draft Report was delayed due to resource constraints and coordination with Department of Interior. A vertically aligned schedule is not available to report at this time. | 2016-06-10: 2016-09-26
| NAD | NAO | Flood Risk Management Studies, Norfolk, VA | 2016-02-03 | 5/9/2016 | 2017-10-03 | 2018-06-14 | 2018-07-19 | 2018-10-18 | 2019-01-31
| NAD |  | Hashamomuck Cove, NY* |  |  | 2015-11-10 | 2016-04-29 | 2016-05-13 | 2016-07-29 | 2016-10-14 | The release of the Draft Report was delayed due to availability of modeling data and beach FX data . A vertically aligned schedule is not available to report at this time. | 2016-06-10: 2016-09-26
| NAD |  | Highlands, NJ* |  |  | 2015-06-30 | 2016-01-08 | 2016-02-08 | 2016-03-04 | 2016-06-15 | The release of the Draft Report was delayed due to complex optimization and economics and resource availability . A vertically aligned schedule is not available to report at this time. | 2016-06-10: 2016-09-26
| NAD |  | Hudson Raritan Estuary - Jamaica Bay, NY, Environmental | 1996-02-01 | 9/11/2015 | 2016-03-29 | 2017-04-13 | 2017-05-13 | 2017-07-21 | 2017-12-20 | The release of the Draft Report was delayed due to formulation concerns and coordination required for consolidation of study efforts under Hudson Raritan Estuary program. A vertically aligned schedule is not available to report at this time. | 2016-06-10: 2016-09-26
| NAD |  | Hudson Raritan Estuary - Bronx River Basin, NY | 2003-11-01 | 9/11/2015 | 2016-03-29 | 2017-04-13 | 2017-05-13 | 2017-07-21 | 2017-12-20 | The release of the Draft Report was delayed due to formulation concerns and coordination required for consolidation of study efforts under Hudson Raritan Estuary program. A vertically aligned schedule is not available to report at this time. | 2016-06-10: 2016-09-26
| NAD |  | Hudson Raritan Estuary - Flushing Bay, NY | 1999-09-01 | 9/11/2015 | 2016-03-29 | 2017-04-13 | 2017-05-13 | 2017-07-21 | 2017-12-20 | The release of the Draft Report was delayed due to formulation concerns and coordination required for consolidation of study efforts under Hudson Raritan Estuary program. A revised schedule is not available to report at this time. | 2016-06-10: 2016-09-26
| NAD |  | Hudson Raritan Estuary - Hackensack | 2003-04-23 | 9/11/2015 | 2016-03-29 | 2017-04-13 | 2017-05-13 | 2017-07-21 | 2017-12-20 | The release of the Draft Report was delayed due to formulation concerns and coordination required for consolidation of study efforts under Hudson Raritan Estuary program. A vertically aligned schedule is not available to report at this time. | 2016-06-10: 2016-09-26
| NAD |  | Hudson Raritan Estuary - Lower Passaic River, NJ | 2003-06-30 | 9/11/2015 | 2016-03-29 | 2017-04-13 | 2017-05-13 | 2017-07-21 | 2017-12-20 | The release of the Draft Report was delayed due to formulation concerns and coordination required for consolidation of study efforts under Hudson Raritan Estuary program. A vertically aligned schedule is not available to report at this time. | 2016-06-10: 2016-09-26
| NAD |  | Hudson Raritan Estuary NY &NJ | 2001-07-12 | 9/11/2015 | 2016-03-29 | 2017-04-13 | 2017-05-13 | 2017-07-21 | 2017-12-20 | The release of the Draft Report was delayed due to formulation concerns and coordination required for consolidation of study efforts under Hudson Raritan Estuary program. A vertically aligned schedule is not available to report at this time. | 2016-06-10: 2016-09-26
| NAD |  | Lake Montauk Harbor, NY* |  |  | 2015-10-20 | 2016-07-12 | 2016-08-02 | 2016-10-03 | 2017-01-06 | The release of the final report has been delayed due to the lack of support for the NED plan by the non-Federal Sponsor and subsequent exploration of at locally preferred plan. A vertically aligned schedule is not available to report at this time. | 2016-06-10: 2016-09-26
| NAD |  | Mamaroneck-Sheldrake Rivers, NY | 2010-03-01 | 9/11/2015 | 2015-12-31 | 2016-05-28 | 2016-06-30 | 2016-07-30 | 2016-09-30 | The release of the Final Report was delayed due to significant public comment, response actions, and additional information needed to confirm the tentatively selected plan. A vertically aligned schedule is not available to report at this time. | 2016-06-10: 2016-09-26
| NAD | NAP | New Jersey Backbay Coastal Resilience Study, NJ | 2016-04-11 | 2016-09-09 | 2017-12-26 | 2018-09-02 | 2018-11-02 | 2018-12-18 | 2019-04-05
| NAD |  | Norfolk Harbor 55-Foot Channel, VA |  |  | 2016-12-20 | 2017-08-01 | 2017-08-14 | 2017-09-14 | 2018-06-01 | Schedule adjustment following Alternatives Milestone Meeting 12/16/2015 | 2016-04-17 | 2017-03-01 | 2017-11-22 | 2017-12-22 | 2018-03-01 | 2018-06-01
| NAD |  | Norfolk Harbor, Eliz River South Branch, VA |  |  | 2016-12-20 | 2017-08-01 | 2017-08-14 | 2017-09-14 | 2018-06-01 | Schedule adjustment following Alternatives Milestone Meeting 12/11/2015 | 2016-04-17 | 2017-03-01 | 2017-11-22 | 2017-12-22 | 2018-03-01 | 2018-06-01
| NAD |  | North Shore of Long Island, Asharoken, NY* |  |  | 2015-08-28 | 2016-03-09 | 2016-03-30 | 2016-05-31 | 2016-08-12 | The release of the Draft Report was delayed due to issues with regard to public access. A vertically aligned schedule is not available to report at this time. | 2016-04-17: 2016-09-26
| NAD |  | North Shore of Long Island, Bayville, NY* |  |  | 2015-08-26 | 2016-05-06 | 2016-05-31 | 2016-08-02 | 2016-09-30 | The feasibility study is terminating, no schedule to report.
444053 | NAD |  | Passaic River Tidal Protection Area* |  |  | 2017-02-26 | 2017-04-05 | 2017-06-06 | 2017-08-29 | 2018-01-28 | The release of the Draft Report was delayed due to New Jersey's letter of support. A vertically aligned schedule is not available to report at this time. | 2016-04-17: 2016-09-26
444633 | NAD |  | Pawcatuck River & Rhode Island Coastal Investigation* |  |  | 2016-01-19 | 2016-10-19 | 2016-11-18 | 2017-01-20 | 2017-04-24 | The release of the Draft Report was delayed due to hydrologic modeling and increased scope of non-structural analysis. | 2016-05-25 | 2016-10-14 | 2017-03-31 | 2017-05-02 | 2017-06-29 | 2017-10-12
395611 | NAD |  | Pine Knot Delaware River Basin | 2008-12-19 | 9/11/2015 | 2016-04-06 | 2016-12-29 | 2017-02-02 | 2017-04-03 | 2017-06-07 | The feasibility study is terminating, no schedule to report. | 2016-05-25: 2016-09-02
| NAD |  | Rahway River Basin, NJ |  |  | 2016-05-31 | 2017-01-31 | 2017-02-28 | 2017-04-28 | 2017-06-30 | The release of the Draft Report was delayed due to Dam Safety concerns that stemmed from proposed modifications to existing structures for the alternatives analysis. A vertically aligned schedule is not available to report at this time. | 2016-05-25: 2016-09-26
| NAD |  | Rahway River Basin, NJ* |  |  | 2016-09-16 | 2017-07-31 | 2017-06-30 | 2017-10-31 | 2018-01-31 | The release of the Draft Report was delayed due to resource constraints . A vertically aligned schedule is not available to report at this time. | 2016-05-25: 2016-09-26
| NAD |  | Rockaway, NY* |  |  | 2015-11-13 | 2016-10-03 | 2016-11-18 | 2017-04-17 | 2017-08-04 | The release of the Draft Report was delayed due to resource constraints and coordination with Department of Interior. A vertically aligned schedule is not available to report at this time. | 2016-05-25: 2016-09-26
| NAD |  | Searsport Harbor, ME | 2005-12-07 | 9/11/2015 | 2013-04-03 | 2015-10-07 | 2015-10-07 | 2015-12-09 | 2016-04-12 | The study has been suspended, no schedule to report.
| NAD |  | Shrewsbury, NJ* |  |  | 2015-08-21 | 2016-04-11 | 2016-03-25 | 2016-05-26 | 2016-08-26 | The release of the Draft Report was delayed due to the requirement of verification of structure in the report. A vertically aligned schedule is not available to report at this time. | 2016-05-25: 2016-09-26
| NAD |  | South Shore of Staten Island, NY* |  |  | 2015-06-12 | 2015-12-07 | 2016-01-05 | 2016-02-08 | 2016-05-20 | The milestones were delayed due to unforeseen issues with the report. | 2016-09-26 | 2015-06-12 | 2016-04-27 | 2016-06-20 | N/A | 2016-10-31
013592 | NAD |  | Westchester County Streams, Byram River, NY | 2012-08-29 | 9/11/2015 | 2016-05-31 | 2017-02-28 | 2017-03-28 | 2017-05-31 | 2017-07-31 | The release of the Draft Report was delayed due to a sponsor request to evaluate an additional alternative after identification of a tentatively-selected plan. A vertically aligned schedule is not available to report at this time. | 2016-05-25: 2016-09-26
| NWD |  | Adams and Denver County, CO | 2014-05-20 | 2015-08-11 | 2016-03-01 | 2016-11-14 | 2016-11-21 | 2017-01-30 | 2017-05-16 | Additional public coordination required. A vertically aligned schedule is not available to report at this time. | 2016-09-23
| NWD |  | Boise River General Investigations Feasibility Study, ID | 2015-01-30 | 2015-06-10 | 2016-02-28 | 2016-12-31 | 2017-01-31 | 2017-03-28 | 2017-06-30 | The feasibility study is terminating, no schedule to report. | 2016-09-23
010625 | NWD |  | Fremont, NE | 2015-07-21 | 2016-08-10 | 2017-04-05 | 2017-12-05 | 2018-01-05 | 2018-03-15 | 2018-06-15
| NWD |  | Lower Dungeness Ecosystem Restoration Study, WA | 2016-03-17 | 2016-08-30 | 2018-01-11 | 2019-05-24 | 2019-06-27 | 2019-09-20 | 2020-01-08
| NWD |  | Lower Willamette River Environmental Dredging, OR | 2003-09-22 | 2015-06-10 | 2014-09-15 | 2015-02-25 | 2015-05-27 | 2015-07-30 | 2015-11-01 | The feasibility study is completed, actual dates reported. |  | 2014-09-15 | 2015-02-25 | 2015-05-27 | 2015-07-30 | 2015-11-01
| NWD |  | Missouri River Bed Degradation, MO | 2010-11-01 | 2012-11-05 | 2017-01-31 | 2017-03-20 | 2017-04-10 | 2017-08-25 | 2017-12-12
| NWD |  | Puget Sound Nearshore Ecosystem Restoration Study, WA | 2001-09-25 | 2015-08-14 | 2014-10-10 | 2016-04-01 | 2016-04-30 | 2016-06-30 | 2016-09-30 | The feasibility study is completed, actual dates reported. |  | 2014-09-26 | 2016-03-28 | 2016-04-27 | 2016-06-29 | 2016-09-30
13767 | NWD |  | Puyallup River Basin Flood Risk Management Feasibility Study, WA | 2010-09-23 | 2016-12-01 | 2016-02-16 | 2017-03-30 | 2017-04-30 | 2017-06-30 | 2017-09-30 | The release of the Draft Report was delayed due to additional engineering modeling required. A vertically aligned schedule is not available at this time. | 2016-09-23
| NWD |  | Seattle Harbor Navigation Improvement Project General Investigation Study, WA | 2014-09-29 | 2014-09-29 | 2016-07-15 | 2017-05-26 | 2017-06-26 | 2017-08-15 | 2017-11-15 | There release date of draft report was delayed due to additional internal review. The accelerated schedule is reported. | 2016-09-23 | 2016-08-02 | 2017-03-15 | 2017-04-14 | 2017-06-15 | 2017-09-29
| NWD |  | Skokomish River Basin Ecosystem Restoration General Investigation Study, WA | 8/12/16 (DA) | 2016-08-12 | 2014-02-14 | 2015-04-16 | 2015-05-26 | 2015-08-25 | 2015-12-31 | The feasibility study is completed, actual dates reported. |  | 2014-01-27 | 2015-04-12 | 2015-04-23 | 2015-08-25 | 2015-12-14
| NWD |  | Upper Turkey Creek Basin, KS |  |  | 2013-11-05 | 2015-03-12 | 2015-03-13 | 2015-05-19 | 2015-11-02 | The feasibility study is completed, actual dates reported. |  | 2013-11-05 | 2015-03-12 | 2015-03-13 | 2015-05-19 | 2015-12-22
007780 | NWD |  | Willamette River Basin Review, OR | 2015-08-19 | 2015-09-29 | 2017-08-08 | 2018-01-31 | 2018-02-28 | 2018-05-18 | 2018-08-17
| POD |  | Ala Wai Canal, HI | 2012-11-08 | 2015-06-09 | 2015-09-01 | 2016-07-01 | 2016-08-01 | 2016-10-01 | 2017-01-01
| POD |  | Alaska Deep Draft Arctic Regional Port System, AK | 2011-12-08 | 2015-06-10 | 2015-02-20 | 2015-09-04 | 2015-09-18 | 2015-11-19 | 2016-02-16 | The feasibility study was put on suspension, no schedule to report.
| POD |  | Craig Harbor, AK | 2012-07-11 | 2015-06-10 | TBD | TBD | TBD | TBD | TBD | The feasibility study is completed, actual dates are reported. | 2015-10-16 | 2015-01-05 | 2015-09-09 | 2015-10-18 | 2015-11-17 | 2016-03-16
| POD |  | Hilo Harbor Modification, HI | 2013-09-30 | 2015-06-09 | 2015-10-05 | 2016-09-23 | 2016-10-14 | 2016-12-14 | 2017-03-14 | The feasibility study is terminating, no schedule to report.
076185 | POD |  | Kenai Bluffs, AK | 2015-05-12 | 2015-08-10 | 2017-03-28 | 2017-05-26 | 2017-06-12 | NA** | NA**
| POD | POA | Kotzebue Navigation Improvement, AK | 2015-11-12 | 2016-02-16 | 2017-05-15 | 2018-05-21 | 2018-05-30 | 2018-07-31 | 2018-10-01
| POD |  | Little Diomede Navigation Improvements, AK | 2006-11-06 | 2015-06-10 | 2013-11-06 | 2014-03-18 | 2014-04-01 | 2015-05-16 | 2015-07-31 | The feasibility study is completed, actual dates are reported. |  | 2013-11-06 | 2014-03-18 | 2014-04-01 | 2015-05-16 | 2015-08-10
397427 | POD | POH | Rota Harbor, CNMI | 2015-12-04 | 2016-03-16 | 2017-07-07 | 2018-05-21 | 2018-06-12 | 2018-09-12 | 2019-01-07
| POD | POA | St. George Navigation Improvement, AK | 2015-10-15 | 2016-02-18 | 2017-05-17 | 2018-04-25 | 2018-05-09 | 2018-07-11 | 2018-09-15
| POD | POH | Tinian Harbor, CNMI | 2015-12-04 | 2016-03-16 | 2017-07-07 | 2018-05-21 | 2018-06-12 | 2018-09-12 | 2019-01-07
012952 | POD |  | Waiakea-Palai FRM, HI | 2012-03-23 | 2015-06-09 | 2015-10-07 | 2016-04-15 | 2016-04-29 | 2016-06-20 | 2016-09-15 | Terminating study and completing in the Continuing Authorities Program, no schedule to report.
| SAD | SAJ | Loxahatchee River Watershed Restoration | 1/21/16*** | 2015-12-18 | 2017-08-10 | 2018-06-12 | 2018-08-03 | 2018-09-24 | 2019-01-09
| SAD | SAJ | Manatee Harbor, FL | 2015-11-10 | 2016-02-10 | 2017-10-27 | N/A | 2018-06-26 | 2018-08-28 | 2018-11-30 | The feasibility study was put on suspension, no schedule to report.
010447 | SAD | SAM | Mobile Harbor, AL | 11/9/2015** | 2016-01-20 | 2018-07-18 | 2019-04-11 | 2019-05-21 | NA** | NA**
403024 | SAD | SAW | Princeville, NC | 2002-07-18 | 2015-08-19 | Completed | 2015-09-04 | 2015-10-07 | 2015-12-08 | 2016-03-10 | The feasibility study is completed, actual dates are reported. |  | 2014-03-25 | 2015-09-04 | 2015-10-07 | 2015-12-09 | 2016-02-23
| SAD | SAM | Proctor Creek, GA | 2015-10-05 | 2015-12-22 | 2017-07-10 | 2018-03-19 | 2018-04-18 | 2018-06-18 | 2018-09-18
| SAD | SAJ | San Juan Harbor Improvements Study | 2015-09-16 | 2015-12-17 | 2017-03-03 | 2018-04-27 | 2018-06-10 | 2018-07-31 | 2018-09-14 | No missed milestones, schedule has been adjusted since the last 1002 Report | 2016-09-19 | 2017-03-03 | 2018-03-15 | 2018-04-15 | 2018-06-15 | 2018-09-14
| SAD | SAJ | St. Johns County Feasibility | 2004-09-22 | 2015-08-07 | 2016-02-17 | 2016-11-22 | 2016-11-30 | 2017-01-31 | 2017-05-08 | No missed milestones, schedule has been adjusted since the last 1002 Report | 2016-09-19 | 2016-02-17 | 2016-11-22 | 2016-12-22 | 2017-02-22 | 2017-05-22
081545 | SAD | SAJ | St. Lucie County Feasibility | 2004-06-29 | 2015-08-07 | 2016-05-03 | 2016-12-06 | 2017-02-07 | 2017-04-18 | 2017-07-25 | No missed milestones, schedule has been adjusted since the last 1002 Report | 2016-09-19 | 2016-05-03 | 2016-12-06 | 2017-02-07 | 2017-04-07 | 2017-07-07
13838 | SAD | SAM | Sweetwater Creek, GA | 2016-05-25 | 2016-08-23 | 2018-03-13 | 2018-10-30 | 2018-11-30 | 2019-01-30 | 2019-04-29
| SPD |  | Aliso Creek Mainstem, CA |  |  | 2015-12-21 | 2016-06-27 | 2016-07-18 | 2016-08-25 | 2016-11-16 | The milestones were delayed due to several issues, one being a potential policy issue with mitigation. A vertically aligned schedule is not available to report at this time.
| SPD |  | Arroyo Seco Watershed, CA |  |  | 2016-05-20 | 2017-01-18 | 2017-02-10 | 2017-04-06 | 2017-07-13 | The milestones were delayed due to delays in determining the tentatively selected plan. A vertically aligned schedule is not available to report at this time.
| SPD | SPL | Carpinteria, CA | 2003-06-26 | 2016-08-19 | 2017-08-07 | 2018-03-30 | 2018-04-13 | 2018-05-24 | 2018-09-11 | No missed milestones, schedule has been adjusted since the last 1002 Report |  | 2018-08-06 | 2019-03-12 | 2019-04-12 | 2019-06-11 | 2019-09-10
| SPD |  | Corte Madera Creek, CA |  |  | 2016-12-15 | 2017-07-21 | 2017-08-04 | 2017-10-19 | 2017-12-20 | No missed milestones, schedule has been adjusted since the last 1002 Report | 2016-09-23 | 2017-03-10 | 2018-02-05 | 2018-03-05 | 2018-05-07 | 2018-08-07
| SPD |  | Dry Creek (Warm Springs) Restoration, CA |  |  | 2016-10-05 | 2017-07-24 | 2017-08-14 | 2017-11-08 | 2018-03-15 | No missed milestones, schedule has been adjusted since the last 1002 Report | 2016-09-23 | 2017-05-19 | 2018-04-10 | 2018-05-10 | 2018-07-10 | 2018-10-10
| SPD | SPL | East San Pedro Bay, CA | 2010-11-10 | 2016-08-19 | 2017-10-23 | 2018-06-07 | 2018-06-21 | 2018-08-02 | 2019-01-11 | No missed milestones, schedule has been adjusted since the last 1002 Report |  | 2017-10-23 | 2018-07-30 | 2018-08-30 | 2018-10-30 | 2019-02-07
443841 | SPD |  | Encinitas/Solana Beaches, CA |  |  | 2013-04-11 | 2014-11-26 | 2015-01-23 | 2015-04-21 | 2015-10-13 | The feasibility study is completed, actual dates are reported. |  | 2013-04-11 | 2014-11-26 | 2015-01-23 | 2015-04-21 | 2016-04-26
| SPD |  | Espanola Valley, Rio Grande and Tributaries, NM |  |  | 2015-09-02 | 2016-10-03 | 2016-04-04 | 2016-06-24 | 2016-10-04 | The milestones were delayed due to delays in determining the tentatively selected plan. A vertically aligned schedule is not available to report at this time.
| SPD |  | Little Colorado (Winslow), AZ |  |  | 2015-11-24 | 2016-01-08 | 2016-02-29 | 2016-09-15 | 2016-12-15 | The release of the Draft Report was delayed due to additional work needed to complete. A vertically aligned schedule is not available to report at this time.
| SPD |  | Los Angeles River Ecosystem Restoration, CA |  |  | 2013-10-01 | 2015-05-15 | 2015-05-18 | 2015-07-16 | 2016-03-14 | The feasibility study is completed, actual dates are reported. |  | 2013-10-01 | 2015-05-15 | 2015-05-18 | 2015-12-18 | 2015-07-17
| SPD |  | Lower Cache Creek, CA |  |  | 2016-02-15 | 2016-11-30 | 2017-01-16 | 2017-04-17 | 2017-07-17 | The study inactive at request of sponsor. A vertically aligned schedule is not available for the report. | 2016-09-21
| SPD |  | Lower San Joaquin, CA |  |  | 2015-04-13 | 2015-11-17 | 2015-12-01 | 2016-02-11 | 2016-06-01 | The release of the Final Report was delayed due to an extended resource agency consultation. A vertically aligned schedule is not available to report at this time. | 2016-09-13
| SPD | SPL | Lower Santa Cruz River, CA | 2015-08-28 | 2016-08-19 | 2017-12-15 | 2018-04-15 | 9/31/18 | 2019-01-15 | 2019-05-15 | No missed milestones, schedule has been adjusted since the last 1002 Report |  | 2017-12-31 | 2019-02-27 | 2019-03-29 | 2019-05-31 | 2019-08-30
| SPD | SPL | Malibu Creek Watershed, CA | 2001-07-30 | 2016-08-19 | 2016-12-14 | 2017-07-12 | 2017-08-24 | 2017-11-22 | 2018-02-28 | No missed milestones, schedule has been adjusted since the last 1002 Report |  | 2016-12-30 | 2017-08-30 | 2017-09-29 | 2017-11-29 | 2018-03-09
| SPD |  | Middle Rio Grande Bernalillo to Belen |  |  | 2016-12-30 | 2017-05-01 | 2017-06-19 | 2017-09-01 | 2018-01-15 | The study is under review, a vertically aligned schedule is not available for the report. | 2016-09-22
| SPD |  | North West El Paso Feasibility Study, NM |  |  | 2017-09-30 | 2017-11-15 | 2018-01-29 | 2018-04-29 | 2018-08-27 | The study is under review, a vertically aligned schedule is not available for the report. | 2016-09-22
| SPD |  | Pajaro River, CA |  |  | 2015-03-16 | 2015-05-16 | 2015-10-16 | 2016-05-17 | 2016-07-17 | The milestones were delayed due to delays in modeling . A vertically aligned schedule is not available to report at this time. | 2016-09-23
114479 | SPD | SPL | Port of Long Beach Navigation Improvements, CA | 2015-08-27 | 2016-08-19 | 2017-04-19 | 2017-10-16 | 2017-11-13 | 2018-01-19 | 2018-07-10 | No missed milestones, schedule has been adjusted since the last 1002 Report |  | 2017-04-30 | 2018-01-29 | 2018-02-28 | 2018-04-30 | 2018-07-30
13010 | SPD | SPL | Prado Basin, CA |  |  | 2016-04-30 | 2016-11-30 | 2016-12-30 | 2017-01-30 | 2017-04-15 | The release of the Draft Report was delayed due to the need for additional coordination on habitat evaluation. Study is under review, a vertically aligned schedule is not available for the report. | 2016-09-21
| SPD |  | Redwood City Harbor, CA |  |  | 2015-07-10 | 2016-01-15 | 2016-02-16 | 2016-04-15 | 2016-07-15 | The feasibility study is terminating, no schedule to report.
| SPD |  | Sacramento Bank Protection GRR, CA |  |  | 2017-03-03 | 2017-11-15 | 2017-12-15 | 2018-02-02 | 2018-06-29
| SPD |  | San Francisco Bay to Stockton, CA |  |  | 2016-06-24 | 2017-03-16 | 2017-04-20 | 2017-06-16 | 2017-11-08 | The release of the Draft Report was delayed due to environmental analysis and scoping discussions. A vertically aligned schedule is not available to report at this time. | 2016-09-23
| SPD |  | San Francisquito Creek, CA |  |  | 2015-01-22 | 2016-04-27 | 2016-06-01 | 2016-07-13 | 2016-08-31 | The release of the Draft Report was delayed due to environmental analysis. A vertically aligned schedule is not available to report at this time. | 2016-09-23
| SPD |  | San Joaquin Delta Islands and Levees, CA |  |  | 2015-04-14 | TBD | TBD | TBD | TBD | The milestone was missed due to a delay in the agreement amendment. A vertically aligned schedule is not available to report at this time.
| SPD |  | South San Francisco Bay Shoreline Study, CA |  |  | Completed | Completed | 2015-09-11 | 2015-10-27 | 2015-12-15 | The feasibility study is completed, actual dates are reported. |  | 2014-12-22 | 2015-07-16 | 2015-07-23 | 2015-09-11 | 2015-12-18
| SPD |  | Sparks Arroyo, TX |  |  | 2016-10-04 | 2017-02-01 | 2017-03-15 | 2017-04-25 | 2017-08-11 | The feasibility study is terminating, no schedule to report. | 2016-09-22
014363 | SPD | SPL | Westminster, CA (East Garden Grove) |  |  | 2016-03-01 | 2016-12-01 | 2017-01-12 | 2017-03-02 | 2017-06-02 | The release of the Draft Report was delayed due to need for additional hydrologic and hydra ling modeling and validation of bridge costs. Study is under review, a vertically aligned schedule is not available for the report. | 2016-09-21
081730 | SPD |  | Yuba River Ecosystem Restoration, CA |  |  | 2016-12-20 | 2017-08-29 | 2017-09-25 | 2017-11-28 | 2018-06-02
| SWD | SWT | Arkansas River Corridor | 2015-05-22 | 2015-05-10 | 2016-07-15 | 2016-11-23 | 2017-05-19 | 2017-07-03 | 2017-10-19 | The release of the Draft Report was delayed due to additional analysis of ecosystem benefits, the adjusted schedule is reported. | 2016-09-01 | 2017-02-06 | 2017-09-25 | 2017-10-17 | 2018-01-23 | 2018-04-12
| SWD | SWG | Coastal Texas Protection, TX | 2015-11-16 | 2016-02-02 | 2018-07-25 | 2020-10-20 | 2020-11-20 | 2021-01-22 | 2021-04-29
| SWD | SWG | Freeport Harbor, TX | 2015-06-10 | 2016-09-05 | 2017-03-02 | 2017-06-29 | 2017-07-17 | 2017-08-14 | 2017-11-03
| SWD | SWG | Houston Galveston Navigation Channels Extension | 2016-02-29 | 2016-09-01 | 2013-03-01 | 2016-09-26 | 2016-10-07 | 2016-11-09 | 2017-04-07
| SWD | SWG | Houston Ship Channel, TX | 2015-11-13 | 2016-02-16 | 2017-05-18 | 2019-05-10 | 2019-06-10 | 2019-07-12 | 2019-10-28
| SWD | SWF | Middle Brazos River, TX | 2005-12-01 | 2015-07-16 | 2016-06-09 | 2016-11-01 | 2016-11-21 | 2017-01-05 | 2017-03-09 | The release of the Draft Report was delayed due to the Sponsor requiring additional time to update state water plan and incorporate into this feasibility report. This study is under review. A vertically aligned schedule is not available to report. | 2016-09-16
| SWD | SWG | Resacas at Brownsville | 2015-08-12 | 2015-11-09 | 2017-02-22 | 2017-11-14 | 2017-12-13 | 2018-03-16 | 2018-06-28
| SWD | SWG | Sabine Pass to Galveston Bay | 2013-01-10 | 2015-09-10 | 2015-09-11 | 2016-04-15 | 2016-05-20 | 2016-07-12 | 2016-09-27 | An exemption was approved on 1 June 2016, which supported additional modeling and engineering design to reduce the level of risk and uncertainty. The revised schedule is reported. | 2016-07-26 | 2015-10-26 | 2017-02-06 | 2017-02-13 | 2017-04-11 | 2017-08-01
081729 | SWD | SWF | Sulphur River Basin | 2012-04-03 | 2013-11-22 | 2015-11-13 | 2016-04-29 | 2016-05-20 | 2016-06-17 | 2016-08-31 | The release of the Draft Report was delayed due to the need to incorporate the dam safety modification study into this study. A vertically aligned schedule is not available to report. | 2016-09-16
| SWD | SWL | Three Rivers, AR | 2015-06-30 | 2015-09-02 | 2017-03-15 | 2018-02-01 | 2018-02-08 | 2018-02-23 | 2018-06-28 | No missed milestones, schedule has been adjusted since the last 1002 Report | 2016-06-16 | 2017-02-09 | 2018-01-18 | 2018-02-15 | 2018-03-27 | 2018-06-29
**** Milestone not required
| * |  | Sandy Supplemental Funded Studies
| ** |  | Milestone is not required